## Groovify Tasks
Task | Status | Owner | On Time? | Due Date | Commit Date | Notes
Create GitHub Repository | Completed | Jace Claassen | On time | 2025-08-29 | 2025-08-29 | Created the Groovify GitHub repository and shared it with Zack and Nevin.
Test Commit | Completed | Zackary Gacnik | On time | 2025-08-29 | 2025-08-29 | Added comment to GroovifyApplication.java to show connectivity.
Test Commit | Completed | Nevin Fullerton | On time | 2025-08-29 | 2025-08-29 | Added comment to GroovifyApplication.java to show connectivity.
Test Commit | Completed | Jace Claassen | On time | 2025-08-29 | 2025-08-29 | Added comment to GroovifyApplication.java to show connectivity.
Figma Page Designs | Completed | Zackary Gacnik | On time | 2025-09-05 | 2025-09-04 | Basic visual designs for what we want our pages to look like.
Refactor Directory | Completed | Jace Claassen | On time | 2025-09-12 | 2025-09-11 | Moved our main code out from the groovify-project directory.
REACT Implementation | Completed | Zackary Gacnik | On time | 2025-09-12 | 2025-09-11 | Put our REACT basic front end on main.
Flowchart Designs | Completed | Nevin Fullerton | On time | 2025-09-12 | 2025-09-11 | Flowchart diagrams for how we want our pages to function.
Landing Page Front End | Completed | Zackary Gacnik | On time | 2025-09-19 | 2025-09-18 | App.jsx and associated CSS file for the Landing Page. Unit test for Landing Page connectivity created as well.
Refactoring REACT Front End | Completed | Zackary Gacnik | Behind | 2025-09-26 | 2025-09-21 | Refactoring our entire project from REACT to basic HTML and CSS.
New Landing Page Front End | Completed | Zackary Gacnik | Behind | 2025-09-26 | 2025-09-23 | Basic HTML outline for our landing page, this commit was essentially to show our transition from REACT to HTML.
Bottom Nav Bar | Completed | Jace Claassen | Behind | 2025-09-26 | 2025-09-24 | Created the nav bar on the bottom of our pages that routes between all of our project pages.
Database Creation | Completed | Nevin Fullerton | On time | 2025-09-26 | 2025-09-25 | MYSQL database created so we can store persistent data for login and register functionalities.
Flowchart Update | Completed | Nevin Fullerton | On time | 2025-09-26 | 2025-09-25 | Updated our flowcharts so that we can now actually see them as files.
Basic Login Functionality | Completed | Zackary Gacnik | On time | 2025-09-26 | 2025-09-25 | Login functionality working with simple routing to success and failure pages.
Data Model Documentation | Completed | Nevin Fullerton | On time | 2025-09-26 | 2025-09-25 | Data model documentation displaying how our tables within our database will work.
Songs Database Connection | Completed | Nevin Fullerton | On time | 2025-10-03 | 2025-09-30 | Created our songs repository and enabled database connection.
Update Data Model | Completed | Nevin Fullerton | On time | 2025-10-03 | 2025-09-30 | Updated our data model to include our songs repository.
Music Functionality | Completed | Nevin Fullerton | On time | 2025-10-03 | 2025-10-02 | Our application now pulls songs from the database and users can now play music on our application.
Profile Page Front End | Completed | Jace Claassen | On time | 2025-10-03 | 2025-10-02 | Profile page displaying user information completed.
Login Back End | Completed | Zackary Gacnik | On time | 2025-10-03 | 2025-10-03 | User login information is now stored in the database with persisted data.
Consistent CSS Styling | Completed | Jace Claassen | On time | 2025-10-03 | 2025-10-03 | Fixed our colors to be consistent throughout all pages.
Session Handling | Completed | Zackary Gacnik | On time | 2025-10-10 | 2025-10-04 | Sessions are working with browser cookies where we can manually change the length of a session once a user logs in.
Profile Page Updates | Completed | Jace Claassen | On time | 2025-10-10 | 2025-10-05 | Added logout and preference functionalities where a user can personalize their profile.
Session Logout Bug | Completed | Jace Claassen | On time | 2025-10-10 | 2025-10-06 | Sessions now end whenever a user logs out through their profile page.
Registration Functionality | Completed | Zackary Gacnik | Behind | 2025-10-10 | 2025-10-06 | Users can now register a new profile and that profile data is persistent with our database.
Media Player Front End | Completed | Nevin Fullerton | Behind | 2025-10-10 | 2025-10-06 | Added HTML for our media player and also fixed a bug where some songs don't show up.
Profile Information Validation | Completed | Jace Claassen | Behind | 2025-10-10 | 2025-10-06 | Added validation checks for when a username or description for a profile is changed.
Updated GANTT Chart | Completed | Zackary Gacnik | Behind | 2025-10-10 | 2025-10-09 | Updated our GANTT chart with everything we have done in the project so far.
Media Player Functionality | Completed | Nevin Fullerton | Behind | 2025-10-10 | 2025-10-10 | Added a pause / play button as well as a progress bar that allows a user to seek within a song. Also added a volume slider to adjust volume.
Register and Login Logging | Completed | Zackary Gacnik | Behind | 2025-10-10 | 2025-10-10 | The application now logs any login or register functionality actively.
JavaDoc For Main Code | Completed | Zackary Gacnik | On time | 2025-10-17 | 2025-10-13 | Added JavaDoc for most of our classes.
Register Functionality Bug | Completed | Zackary Gacnik | On time | 2025-10-17 | 2025-10-13 | Now you don't get a white label error whenever a user doesn't enter in valid login information.
Music Import Upon Launch | Completed | Nevin Fullerton | On time | 2025-10-17 | 2025-10-15 | Added a script that will load music upon web application launch.
Genre Selection | Completed | Jace Claassen | On time | 2025-10-24 | 2025-10-23 | Added a preferred genres selection in the profile page. Also adjusted the logout functionality, where there is now a dropdown menu when you click the profile button.
Updated Nav Bar CSS | Completed | Jace Claassen | On time | 2025-10-24 | 2025-10-24 | Changed the CSS on the nav bar to look better, as well as with the profile page.
Home Page Template | Completed | Jace Claassen | On time | 2025-10-24 | 2025-10-24 | Created a template for the home page and most functionality for the developer section.
Landing Page Unit Test | Completed | Zackary Gacnik | On time | 2025-10-24 | 2025-10-24 | Unit test to check connection to the Landing Page.
Login Unit Test | Completed | Zackary Gacnik | On time | 2025-10-24 | 2025-10-24 | Multiple unit tests to check the login functionality from the Landing Page.
Remove Friends Page | Completed | Jace Claassen | Behind | 2025-10-31 | 2025-10-27 | Removed the Friends page and all associating functionality.
Client Table Refactoring | Completed | Nevin Fullerton | Behind | 2025-10-31 | 2025-10-28 | Refactored all code the pull data from a Client table instead of our old Users table.
Update Data Model | Completed | Nevin Fullerton | Behind | 2025-10-31 | 2025-10-28 | Updated our data model to fit our Client table.
Finalized Profile CSS | Completed | Jace Claassen | On time | 2025-10-31 | 2025-10-28 | Finalized the CSS for the profile page where it fits all screen ratios.
Add Country and Tech Songs | Completed | Jace Claassen | On time | 2025-10-31 | 2025-10-29 | Added 10 country and tech songs to the directory.
Songs Page Update | Completed | Jace Claassen | On time | 2025-10-31 | 2025-10-29 | Updated our song import functionality and created a song fragment.
Add Rock and Classical Songs | Completed | Nevin Fullerton | On time | 2025-10-31 | 2025-10-30 | Added 10 rock and classical songs to the directory.
Add Folk and Pop Songs | Completed | Zackary Gacnik | On time | 2025-10-31 | 2025-10-30 | Added 10 folk and pop songs to the directory.
Controller Class Unit Tests | Completed | Nevin Fullerton | On time | 2025-10-31 | 2025-10-30 | Added unit tests for all of our controller classes.
Finalized Search Page | Completed | Jace Claassen | On time | 2025-10-31 | 2025-10-30 | Improved CSS and media bar and search functionality complete.
Password Hashing | Completed | Zackary Gacnik | On time | 2025-10-31 | 2025-10-30 | Passwords are now hashed with SHA-256 algorithm, a salt is included as well.
Redirect Bug | Completed | Zackary Gacnik | On time | 2025-10-31 | 2025-10-30 | Fixed a redirect bug where there was a conflict between Windows and MAC.
Genre Unit Test | Completed | Jace Claassen | On time | 2025-10-31 | 2025-10-31 | Added a unit test for the genre functionality.
Register Functionality Comprehensive Unit Test | Completed | Zackary Gacnik | On time | 2025-10-31 | 2025-10-31 | Good, bad, and really bad paths covered by unit tests for the register functionality.
GANTT Chart Update | Completed | Zackary Gacnik | On time | 2025-10-31 | 2025-10-31 | Updated our GANTT chart to current status.
Update Figma Documentation | Completed | Zackary Gacnik | On time | 2025-10-31 | 2025-10-31 | Updated our Figma images to screenshots of the physical pages on our web application.
Songs Page Update | Completed | Jace Claassen | On time | 2025-11-07 | 2025-11-05 | Scroll arrows work on the songs page.
Home Page Update | Completed | Jace Claassen | On time | 2025-11-07 | 2025-11-05 | Recommended songs by genre are shown on the home page, and you can now search by genre.
Song Artist | Completed | Jace Claassen | On time | 2025-11-07 | 2025-11-05 | Randomly assigns a first and last name as the artist of all the songs.
Service Unit Tests | Completed | Jace Claassen | On time | 2025-11-07 |  | Unit tests for services
Register Service Comprehensive Unit Test | Completed | Zackary Gacnik | On time | 2025-11-10 | 2025-11-09 | Comprehensive unit test for the Register Service covering all methods with 20 tests per method.
Developer Manual | Completed | Zackary Gacnik | On time | 2025-11-10 | 2025-11-08 | Created a developer manual that walks people through how to boot up our program - downloads needed, console commands to get it linked, etc..
Regex Utility | Completed | Zackary Gacnik | On time | 2025-11-14 | 2025-11-14 | Regex utility to only allow certain criteria for username and password input upon registration.
Cookie Bug Fix | Completed | Zackary Gacnik | On time | 2025-11-21 | 2025-11-15 | Fixed a bug where the cookie data was not being sent to the browser.
Client Update | Completed | Zackary Gacnik | On time | 2025-11-21 | 2025-11-15 | Changed the Client class to not have SQL stuff to help improve security.
Playlist UnitTest | Completed | Nevin Fullerton | On time | 2025-11-21 | 2025-11-21 | Unit test for playlist service
Genre Import Tests | Completed | Jace Claassen | On time | 2025-11-23 | 2025-11-21 | Unit tests for genre import completed with javadoc
Profile Tests | Completed | Jace Claassen | On time | 2025-11-23 | 2025-11-21 | Unit tests for profile service completed with javadoc
Recommendation Tests | Completed | Jace Claassen | On time | 2025-11-23 | 2025-11-21 | Unit tests for recommendation service completed with javadoc
Login Tests | Completed | Jace Claassen | On time | 2025-11-23 | 2025-11-21 | Unit tests for login service completed with javadoc
Song UnitTest | Completed | Nevin Fullerton | On time | 2025-11-23 | 2025-11-23 | Unit test for song service
Developer Manual Update | Completed | Zackary Gacnik | On time | 2025-11-24 | 2025-11-23 | One final update to the developer manual to include correct MySQL setup information.